## Test Plan
SYSTEM: | Application backend Users
OBJECTIVE OF THE DOCUMENT
The objective of this test plan is to verify the correct functioning of the backend of the user application for the company Mieles S.AS.
Summary of functionality: | Automate the backend of the company Mieles SAS for its user management.
ALCANCE
scope: | This test plan will cover the following backend areas:
Functionality
Error handling
Risk:
* Instability in the test environment.
* Network availability.
* Availability of services.
Out of reach: | • Validations not described within the Specification documents.
• Modifications not described in this document.
• No performance tests shall be performed.
• No security testing shall be performed.
Note: The scope defined in this test is made taking into account the information provided in use cases, supplementary specifications, FSP, CHR, development handover minutes, and unit tests. The scope of this test does not include the following functionalities no descritas o ya existentes.
STRATEGY
1. Identifying Requirements and Functionalities
Understand the backend requirements and functionalities to be tested (post,get,put,delete).
Identify the API endpoints to be tested.
2. Test Environment Preparation
Install and configure Karate in the development environment.
3.Test Case Development
Write test cases using Gherkin syntax to describe the expected behaviour of the backend.
Use Karate's capabilities to make HTTP requests to API endpoints and validate the responses received.
Include test scenarios to cover different test cases, including success cases, error cases, and test cases for the backend.
4. Test Execution
Verify that all test cases are executed correctly and that there are no validation errors.
5. Report Generation
Generate detailed test reports using Karate's reporting capabilities.
Use the reports to identify failed test cases and to communicate test results to the development team and other stakeholders.

## Test Cases
Test Cases
Project name | Automatizacion Backend modulo Usuarios
Responsable: | Juan Felipe Silva
Date of creation: | 2024-05-08
Name Test Case | Description Test Case | Precondition <NA / precondition>. | Priority <High, Medium, Low>. | No. Step | Description of the Pass | Expected Result
Create new user | the https://reqres.in/api/users service should allow the creation of new users by generating a unique user ID. | previously unregistered user | H | 1 | send post type request to the service https://reqres.in/api/users | the service shall allow to send a new name and a new job within the request body
|  |  |  | 2 | Validate http code is 201 | the service shall respond with an htpp code 201
Response validation on user creation | validate that the structure of the response is correct according to the swagger specification. | user successfully created and http code= 201 | M | 1 | send post type request to service https://reqres.in/api/users | the service shall allow to send a new name and a new job within the request body
|  |  |  | 2 | Validate response structure | the service shall respond with the fields "name", "job", "id", "createdAt", all of type string
Query existing user | the service https://reqres.in/api/users/2 shall return the ID information sent as query parameter | user successfully created and http code= 201 | H | 1 | send get type request to https://reqres.in/api/users/ID service | the service shall allow querying the user by means of the user ID
|  |  |  | 2 | Validate http code is 200 | the service shall return with a http code = 200 and the client information such as first name last name email id avatar inside an object called data
Update existing user | the service https://reqres.in/api/users/ID shall return the name, job and date of update of the ID associated with that user | user successfully created and http code= 201 | H | 1 | send put type request to https://reqres.in/api/users/ID service | the service shall allow to update the fields name and job with the new values
|  |  |  | 2 | Validate http code sea 200 | the service shall return with an http code = 200 and the client information such as job name and update date
Delete user | the https://reqres.in/api/users/2 service shall remove from the list the user with the ID sent as a parameter | user successfully created and http code= 201 | H | 1 | Validate http code is 204 | the service shall return with an http code = 204
Update non-existing user | the https://reqres.in/api/users/ID service shall retune with the name, job and update date of the ID associated with that user | user successfully created and http code= 201 | M | 1 | send put type request to https://reqres.in/api/users/ID service | the service should return with an error mentioning that the user does not exist
|  |  |  | 2 | Validate http code is 404 | the service should return with an http code = 404 not found
Query all users | the service https://reqres.in/api/unknown shall return a list of clients. | Previously created users | M | 1 | send get request to https://reqres.in/api/unknown service | the service should allow querying the total number of users
|  |  |  | 2 | Validate http code is 200 | the service should return with an http code = 200 and the clients information as first name last name email id avatar inside an object called data

## Bugs
ID | 1
Title | Allows to update user that does not exist in the list.
Description | the service https://reqres.in/api/users/ID allows to update users that are not previously registered in the list, a code http= 404 not found was expected, however a http code = 200 was obtained.
Data | ID=100000 "name": "Juan felipe", "job": "QA Automation"
Steps | Descripcion | estatus
1 | the fields to be updated | OK
2 | send put request to the endpoint https://reqres.in/api/users/100000000 | OK
3 | validate response 404 | Fallido